## Data
BuHu | Hours | Task-Estimated | 90 | 60 | 90 | 60 | 90 | 60
|  | Task-Actual | 90 | 60 | 90 | 60 | 90 | 60
| Story Points | Planned USP | 9 | 6 | 9 | 6 | 9 | 6
|  | Actual USP | 9 | 6 | 9 | 6 | 9 | 6
| Defects | Valid | 0 | 1 | 0 | 1 | 0 | 1
|  | Found | 0 | 1 | 0 | 1 | 0 | 1
| Code Coverage | Planned | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
|  | Actual | 0.9 | 0 | 1 | 0 | 0.7 | 0
Master Data | [8 empty] | 10 hrs per User Story points
| Productivity(hrs/usp) |  | 10 | 10 | 10 | 10 | 10 | 10 | 6 hrs per day team productivity
| Internal Defect Density(Valid defects/Actual USP) |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | Code Coverage 80%
| Code Coverage |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
| Schedule Variance |  | 0 | 0 | 0 | 0 | 0 | 0
| Productivity Efforts (Planned Hrs- Actual Hrs) |  | 0 | 0 | 0 | 0 | 0 | 0
Note on M4: Vohra, Neeraj: Total PSI Velocity Inclluding Maintenance

## BuHu
Team Productivity( Actual Hrs/US completed)
Phase | Activity | Week | Week | Week | Week | Week | Week | Planned | 10 | 10 | 10 | 10 | 10 | 10
|  | 1 | 2 | 3 | 4 | 5 | 6 | Actual | 10 | 10 | 10 | 10 | 10 | 10
PSI Planning | Planned USP at the start of the Week | 9 | 6 | 9 | 6 | 9 | 6
| Planned Hrs at the start of the Week | 90 | 60 | 90 | 60 | 90 | 60
Sprint Execution | Total Number Of Valid defects in Week | 0 | 1 | 0 | 1 | 0 | 1
| Actual Hrs at the end of the Week | 90 | 60 | 90 | 60 | 90 | 60
| Actual USP completedat the end of the Week | 9 | 6 | 9 | 6 | 9 | 6
| Code Coverage (Sonar) | 0.9 | 0 | 1 | 0 | 0.7 | 0
Inspect and Adapt | Actual Team Productivity | 10 | 10 | 10 | 10 | 10 | 10
| Actual Defect Density | 0 | 0.16667 | 0 | 0.16667 | 0 | 0.16667
| Schedule Variance( actual-planned) | 0 | 0 | 0 | 0 | 0 | 0
| Productivity Efforts( planned hours-actual hrs) | 0 | 0 | 0 | 0 | 0 | 0 | Defect Density( Valid Defect/US Completed)
[8 empty] | Planned | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
[8 empty] | Actual | 0 | 0.16667 | 0 | 0.16667 | 0 | 0.16667
Schedule Slipage( actual USP-planned USP)
[8 empty] | Planned | 9 | 6 | 9 | 6 | 9 | 6
[8 empty] | Actual | 9 | 6 | 9 | 6 | 9 | 6
Productivity Efforts( planned hrs-actual hrs)
[8 empty] | Planned | 90 | 60 | 90 | 60 | 90 | 60
[8 empty] | Actual | 90 | 60 | 90 | 60 | 90 | 60
Sonar Code Coverage( actual-planned)
[8 empty] | Planned | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
[8 empty] | Actual | 0.9 | 0 | 1 | 0 | 0.7 | 0
Note on D17: Vohra, Neeraj: Three new team members

## Jira
Week | US id | Task Id | Subtask Id | Planned Hrs | Actual Hrs | Assigned to | remark
1 | ES-463
1 |  |  | 487 |  |  | Neha Jain | Database setup changed, Offshore team stuck because they were not aware about that.
1 |  |  | 488 |  |  | Neha Jain
1 |  |  | 489 |  |  | Tushar Bhardwaj
1 |  |  | 490 |  |  | Tushar Bhardwaj
1 |  |  | 491 |  |  | Poonam Malwal
|  |  | 492 |  |  | Poonam Malwal