## Sprint3
What Went Well | What didn't go well | ActionItems | Owner
Learning curve of team is good. | Delay in environment setup for new team members. | Documenttation - New Environment setUp | Neeraj,Shweta,Tushar
|  | At time of machine allocation, below action should be performed 1) Machine assignment. 2)Mobile Number Must be updated. | Gaurav
| Regression test suite | Good to have a tester in team.
| Business Knowledge | Business Understanding | Send mail to Gaurav to arrange some business functionality
| Knowledge Sharing Sessions | Documentation -Details Of train and transport events requests. | Ziaul
|  | Documentation - How to convert Swagger JSON to java object. | Poonam/Neha

## Sprint4
Open Items since last sprints
What Went Well | What didn't go well | ActionItems | Status/Remark | Owner
Learning curve of team is good. | Delay in environment setup for new team members. | Documenttation - New Environment setUp | WIP | Neeraj,Shweta,Tushar
|  | At time of machine allocation, below action should be performed 1) Machine assignment. 2)Mobile Number Must be updated. |  | Gaurav
| Regression test suite | Good to have a tester in team.
| Business Knowledge | Business Understanding |  | Send mail to Gaurav to arrange some business functionality
| Knowledge Sharing Sessions | Documentation -Details Of train and transport events requests. | Open | Ziaul
|  | Documentation - How to convert Swagger JSON to java object. |  | Poonam/Neha
|  | Documentation - How to convert xsd to java object. | Open | Poonam/Neha
Current Sprint 4
| Estimation Without Analysis | DOR-Defination of Readyness | Take time of analysis before commitment. | Team
| Delay in Query raising |  | Proper Analysis before making US actionable. | Team
| Quality Of Code | DOD-Defination Of Done Peer Review | TL must have to do peer review | Poonam,Neha
| Request of all scenarios during Demo |  | Request of all scenarios must be created before demo.
| Leaves |  | Share planned leaves in Advance
| Delay in getting response from DBS Helpdesk |  | send reminder mails.

## Sprint5
What Went Well | What didn't go well | ActionItems | Status/Remark | Owner
Open Items since last sprints
| Estimation Without Analysis | DOR-Defination of Readyness | Take time of analysis before commitment. | Team
| Delay in Query raising |  | Proper Analysis before making US actionable. | Team
| Quality Of Code | DOD-Defination Of Done Peer Review | TL must have to do peer review | Poonam,Neha
Current Sprint 5
Team Learnings | Performance Issue |  | Team is doing Anlysis. | Poonam, Neha
| KT sessions | Document Of Rest Flow (Swagger) |  | Tushar
|  | Document Of SOAP flow |  | Shweta

## DOR
Agenda- Making US actionable
S.No | Check Points | Green/Amber/Red
1 | Is business requirement clear?
2 | Is Impact Analysis done ?
3 | Are all dependencies are discussed with stakeholders?
4 | All open queries are closed?
5 | Estimation include testing.

## DOD
Agenda- Making US actionable
S.No | Check Points | Yes/No
1 | Coding done as per acceptance criteria.
2 | Is Impact Analysis done ?
3 | Peer Review Done?
5 | All comments are incorporated
6 | Testing of all scenarios completed.
7 | Request of all scenarios provided by developer.
8 | Testing in integration environment by developer.