## Backlog Refinement
Agenda- Pull the US for next sprint (Backlog prepration)
S.No | Check Points | Owner | Green/Amber/Red | Remark
1 | Backlog already prepared as per priority Items
2 | Team will pick US one by one and PO will explain each US |  |  | No Estimation during Refinement session.
3 | Will prefer one techincal debt in team's backlog, if required.

## Daily Standup-Sprint Status
Agenda- Transparncy with in the team
S.No | Check Points | Owner | Green/Amber/Red | Remark
1 | Only developer will give the status of the current sprint.
2 | If any Query on the backlog Item team will ask from the owner of the US.

## DOR-Sprint Planning
Agenda- Making US actionable as per teams DOR (Sprint planning)
S.No | Check Points | Owner | Green/Amber/Red | Remark
1 | Is acceptance criteria of the US clear to team?
2 | Is all the dependencies are Identified and all stakeholders are aware?
3 | Is there any impediment? If yes then mitigation plan on place
4 | All open queries are answered?
5 | Is DOD is clear to team?
6 | Estimation done by team and accepted by PO.
7 | Is teams confidence voting >3
8 | 1 day as a IP ( Inovation and planning)

## DOD-Sprint Review
Agenda- Making US acceptable as per definition of done ( sprint review meeting)
S.No | Check Points | Owner | Green/Amber/Red | Remark
Initiate | Is new branch created as per the standards? PSEUD-xxx number + some words of description. | PSEUD-789-implementation-of-qwertz. PSEUD-456-bugfix-abc
Create a Merge Request
Act | Adherence to coding standards
Code is unit tested where applicable
Cannot have showstopper/critical defects
100% of planned scenarios pass with some exceptions These exceptions must be reviewed with the PO
Peer Review Done?
| If Need deployment in IAT for Testing ? | Run the pipeline against existing MR, (always finish manual steps of the pipeline when done with testing)
| Check WhiteSource? | Alternative Sprints
| SonarQube | Part of DOD
| Is Commit Message Meaningful | must be related to the actual commit
Code Coverage greater than 80%
All feedback comments are incorporated
All comunication must be on group chat/mail.
Closure | Merge the Integration branch with your branch | Solve the conflict if any
Update status of corresponding JIRA task to 'Review'
| Is corresponding branch merged with Integration branch? | Validate that your task merged in Integration branch
| Is cleanup activity done? | Your branch is deleted

## Retrospective
Agenda- Learning from previous sprints, Action Items for continuous Improvement,Identification of wastage ( open defects, un complete user stories,stories moved to next sprint..etc)
S.No | Check Points | Owner | Green/Amber/Red | Remark
What Went Well | What didn't go well | ActionItems | Owner
Sprint cermonies followed effectively. | US moved to next sprint.
Dependencies Identified during execution.
Sprint review did not went well.