## Data
DBS | Hours | Task-Estimated | 90 | 60 | 90 | 60 | 90 | 60
|  | Task-Actual | 90 | 60 | 90 | 60 | 90 | 60
| Story Points | Planned USP | 9 | 6 | 9 | 6 | 9 | 6
|  | Actual USP | 9 | 6 | 9 | 6 | 9 | 6
| Defects | Valid | 0 | 1 | 0 | 1 | 0 | 1
|  | Found | 0 | 1 | 0 | 1 | 0 | 1
| Code Coverage | Planned | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
|  | Actual | 0.9 | 0 | 1 | 0 | 0.7 | 0
| Capacity | Available
Consumed
Master Data- Baseline | [8 empty] | 10 hrs per User Story points
| Productivity(Actual hrs/Actual USP) |  | 10 | 10 | 10 | 10 | 10 | 10 | 6 hrs per day team productivity
| Internal Defect Density(Valid defects/Actual USP) |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | Code Coverage 80%
| Code Coverage |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
| Schedule Variance(actualUSP-planned USP) |  | 0 | 0 | 0 | 0 | 0 | 0
| Productivity Efforts (Planned Hrs- Actual Hrs) |  | 0 | 0 | 0 | 0 | 0 | 0
| Efforts Utilization(Actual Hours/Idle Capacity) |  | 1 | 1 | 1 | 1 | 1 | 1
Note on M4: Vohra, Neeraj: Total PSI Velocity Inclluding Maintenance

## BuHu
Team Productivity( Actual Hrs/US completed)
Phase | Activity | Week | Week | Week | Week | Week | Week | Planned | 10 | 10 | 10 | 10 | 10 | 10
|  | 1 | 2 | 3 | 4 | 5 | 6 | Actual | 10 | 6.6667 | 10 | 6.6667 | 10 | 6.6667
PSI Planning | Planned USP at the start of the Week | 9 | 9 | 9 | 9 | 9 | 9
| Planned Hrs at the start of the Week | 90 | 60 | 90 | 60 | 90 | 60
| Idle capacity at the start of the week | 50 | 50 | 50 | 50 | 50 | 50
Sprint Execution | Actual USP completedat the end of the Week | 9 | 9 | 9 | 9 | 9 | 9
| Actual Hrs at the end of the Week | 90 | 60 | 90 | 60 | 90 | 60
| Total Number Of Valid defects in Week | 9 | 6 | 9 | 6 | 9 | 6
| Actual Code Coverage (Sonar) | 0.9 | 0 | 1 | 0 | 0.7 | 0
Inspect and Adapt | Productivity(Actual hrs/Actual USP) | 10 | 6.6667 | 10 | 6.6667 | 10 | 6.6667
| Internal Defect Density(Valid defects/Actual USP) | 1 | 0.66667 | 1 | 0.66667 | 1 | 0.66667
| Schedule Variance(actualUSP-planned USP) | 0 | 0 | 0 | 0 | 0 | 0
| Productivity Efforts (Planned Hrs- Actual Hrs) | 0 | 0 | 0 | 0 | 0 | 0 | Internal Defect Density( Valid Defect/US Completed)
| Efforts Utilization(Actual Hours/Idle Capacity) | 1.8 | 1.2 | 1.8 | 1.2 | 1.8 | 1.2
[8 empty] | Planned | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
[8 empty] | Actual | 1 | 0.66667 | 1 | 0.66667 | 1 | 0.66667
Schedule Slipage( actual USP-planned USP)
[8 empty] | Planned | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0
Productivity Efforts( planned hrs-actual hrs)
[8 empty] | Planned | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0
Sonar Code Coverage( actual-planned)
[8 empty] | Planned | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
[8 empty] | Actual | 0.9 | 0 | 1 | 0 | 0.7 | 0
Efforts Utilization(Actual Hours/Idle Capacity)
[8 empty] | Planned | 1 | 1 | 1 | 1 | 1 | 1
[8 empty] | Actual | 1.8 | 1.2 | 1.8 | 1.2 | 1.8 | 1.2

## Capacity Planning
Consultant Name | Role | % Allocation | Business Hours/Day | Sprint Duration | Holiday/Leave | Available Hours/Sprint | Ceremonies Time(7%) | Available Hours (after ceremonies) | Idle Hours 80% | Idle Number Of Days
Dev1 | Dev | 100 | 8 | 10 | 1 | 72 | 5.04 | 66.96 | 53.568 | 6.696
Dev2 | Dev | 100 | 8 | 10 | 1 | 72 | 5.04 | 66.96 | 53.568 | 6.696
Dev3 | Dev | 100 | 8 | 10 | 2 | 64 | 4.48 | 59.52 | 47.616 | 5.952
Dev4 | Dev | 100 | 8 | 10 | 0 | 80 | 5.6 | 74.4 | 59.52 | 7.44
PO | PO | 50 | 8 | 10 | 0 | 40 | 2.8 | 37.2 | 29.76 | 3.72
SM | SM | 25 | 8 | 10 | 0 | 20 | 1.4 | 18.6 | 14.88 | 1.86
[7 empty] | 0 | 0 | 0 | 0
Total |  |  |  | 60 | 4 | 348 | 24.36 | 323.64 | 258.912 | 32.364

## Sheet1
Velocity- How much value we deliver per sprint?
Capacity- How much efforts can we expend in a Sprint?
Focus Factor- What percentage of our efforts becomes values?
Productive Hours?
Estimated Accuracy?
Forecast Accuracy?
Velocity Increase?